## Sheet1
Week 1: | Project Setup and Create an ASP.NET Core MVC Project named "BTRS." Set up a SQL Server database named "BTRS." | Anas
Day 1-2: | Passenger Pages Design and Identify and design all required passenger pages. Create digital sketches using tools like MS Paint, Figma, or by hand. | Xena
Day 3-4: | Model Classes Development and Develop model classes in the "model" folder. Add attributes and constraints using annotation classes. | Anas
Day 5-7: | Database Integration and Connect the web application with the "BTRS" database using Entity Framework Core. Configure EF Core to map model classes to database tables. Handle migrations for database schema changes. | Anas
Day 8-9: | Passenger Views Implementation and mplement passenger views using HTML helpers with Bootstrap for styling. Include functionality and validation to prevent duplicates and handle empty inputs. | Xena
| It Requires a Password for Security. Done | Xena
Week 2 | • Do not register any member with the same email. Done | Xena
Day 1-3 | • If the member fill the Gender, fill it with “Male of Female”. Done | Xena
Day 4-5: | Project Presentation Create a PowerPoint presentation with sections: Introduction, Problem, Solution, Development Process, Suggestions for Enhancement. | Xena
Day 6-8: | GitHub Repository | Xena Anas
| Task Management Tool Excel sheet | Xena